## Evaluation Report
Performance Evaluation Report
Setsoto Municipality (FS191)
Q1 (July- Sept)
Output as per support plan | Output achieved | Allocation as per Support Plan | Allocation spent to date | Allocation still to be spent | Reasons for non achievement of output | Remedial Measures to be implemented | Date when output will be achieved
Salaries of Interns | Yes | 480000 | 124390 | 355610 | N/A | N/A | 2016-06-30
Training towards achieving Minimum Competency | Partially | 220000 | 176154 | 43846 | Interns registration is still pending | Finalise interns' registration | 2016-01-31
Implementaation of MSCOA | No | 900000 | 0 | 900000
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Signature | Date
Municipal Manager
Chief Financial Officer
Note on A3: Select a Quarter from drop down list

## Cash Flow Projection
XXX Municipality Cash Flow Projection
|  | Quarter 1 |  |  | Q2 |  |  | Q3 |  |  | Q4
Output as per support plan | Allocation still to be spent | July | August | September | October | November | December | January | February | March | April | May | June | Balance Outstanding
#REF! | 355610 | [12 empty] | 355610
Training towards achieving Minimum Competency | 43846 | [12 empty] | 43846
Implementaation of MSCOA | 900000 | [12 empty] | 900000
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
0 | 0 | [12 empty] | 0
| Signature | Quarter 1 July: Date
Municipal Manager
Chief Financial Officer